Casa Crobu Market Capture Pilot Plan

A summer market plan to capture customers, learn what works at the booth, and convert that audience into fall delivery demand.

Overview

Casa Crobu has proven market demand. The opportunity now is to stop letting so much of that demand stay anonymous.

From the Shopify/POS data reviewed for May 2024 through March 2026, the biggest finding is that most market buyers are not currently tied to a customer profile or email address. That means Casa Crobu cannot reliably follow up, measure repeat behavior, learn which buyers are returning, or transition those shoppers into online ordering and fall delivery.

The recommended next step is a focused market capture pilot built around Lid Stickers + Market QR Codes, email/SMS consent, summer market experimentation, and a fall delivery conversion plan.

Key Findings

Metric

Finding

Orders analyzed

36,031

Total order-level revenue

$1.59M

POS revenue

$1.17M

All orders anonymous

83.25%

POS orders anonymous

91.62%

Anonymous POS orders

29,621

Known POS order share

8.38%

The 8.38% known POS order share is not active booth capture. It only means that 2,709 POS orders already had an email or Shopify customer profile attached. There is not currently a deliberate system at the booth to capture and consent market shoppers.

Why It Matters

For anonymous market orders, average order value is almost all we know.

Segment

Orders

AOV

Known Customers

Repeat Behavior

Customer LTV

What It Means

Anonymous Market Orders

29,621

$35.73

?

?

?

We cannot reliably follow up, measure repeat visits, or connect market behavior to online conversion.

Known Market Only

2,405

$39.22

1,827

1.32 orders/customer

$51.63

They bought at market and are identifiable, but not yet online buyers.

Online Only

2,912

$114.72

1,368

2.13 orders/customer

$244.20

They have stronger repeat behavior and higher average LTV.

Known Market + Online

677

$87.52

154

4.40 orders/customer

$384.76

These customers are about 7.5x more valuable than Known Market Only.

The customer value gap used in the opportunity model is:

$384.76 Known Market + Online LTV

-$51.63 Known Market Only LTV

= $333.13 observed customer value gap

This is directional, not guaranteed future revenue. Recurring delivery or subscription behavior would be upside beyond this base model.

Base-Case Opportunity Model

Scenario

New Contacts

Online Buyers

Base LTV Upside

Capture 5% of anonymous POS orders; 5% convert online

1,481

74

About $24.7K

Capture 10%; 10% convert online

2,962

296

About $98.7K

Capture 15%; 10% convert online

4,443

444

About $148.0K

Capture 20%; 10% convert online

5,924

592

About $197.4K

29,621 anonymous POS orders

x capture rate

x online conversion rate

x $333.13 observed customer value gap

= base LTV upside

Recommended Pilot

Step

Focus

What It Means

1

Capture

Lid Stickers + Market QR Codes give market shoppers a simple reason to identify themselves.

2

Consent

Collect email first, make SMS optional, and route new signups into the right email/SMS system with the right consent status.

3

Activate

Use the welcome flow and summer market offers to train the list to open, click, and redeem.

4

Convert To Delivery

Turn summer response data into personalized fall delivery bundles, freezer-stock boxes, and recurring order tests.

Klaviyo is the recommended path if account setup and cost make sense. A lighter Shopify-first path is possible if the first test needs to stay simpler.

Three-Phase Project Structure

Phase

Focus

What It Means

Phase 1: Prep + Capture Infrastructure

Set up the system before the pilot markets launch.

QR/signup path, consent handling, email/SMS setup, source tags, first offer mechanics, welcome flow, and basic tracking.

Phase 2: Summer Experimentation

Use the market list during the summer and learn what works.

Weekly specials, pre-reserve tests, offer response, unsubscribe monitoring, product interest, market-by-market learning, and a 45-minute weekly sync if I am supporting activation.

Phase 3: Fall Delivery Conversion

Turn summer engagement into delivery demand.

Personalized fall delivery offer, freezer-stock bundle, recurring order test, and transition messaging.

Sample Summer Flow

Moment

Example

Welcome + Consent

"You're on the Casa Crobu market list. We'll send market specials, preorder drops, and delivery updates. Reply STOP to opt out."

Pizzetta Deal

Test a simple market-list offer or preorder hook that teaches shoppers there is a reason to open Casa Crobu messages.

Weekly Market Special

Example: City Park special or pre-reserve test for the week, with or without a discount, while watching clicks, redemptions, replies, and unsubscribes.

Fall Delivery Offer

Send a summer thank-you and wind-down flow, then move customers into personalized fall delivery bundles or recurring order tests.

Final SMS copy should be reviewed against Klaviyo SMS disclosure setup and Casa Crobu's privacy/terms pages before launch.

What We Learn This Summer

Signal

What We Learn

How It Shapes Fall

Measured In

QR and signup source

Which markets, sticker placements, and staff prompts create the most opt-ins.

Focus the fall push on the audiences and markets already responding.

Email/SMS source tags + Shopify POS counts

Offer response

Whether shoppers respond better to pizzetta deals, preorder hooks, bundles, or threshold discounts.

Use the winning offer style in the fall delivery launch.

Clicks, redemptions, replies, and unsubscribes

Product interest

Which products get attention when we promote specials, preorders, or bundle previews.

Create personalized freezer-stock boxes and delivery bundles around proven interest.

Product clicks, discount usage, and online orders

Delivery intent

Who clicks delivery, preorder, freezer-stock, or recurring bundle messages before markets slow down.

Send a summer thank-you and wind-down flow with a personalized fall delivery offer.

Email/SMS segments + Shopify order history

Responsibility Breakdown

Workstream

My Responsibility

Casa Crobu Responsibility

Output

Platform decision

Review current Shopify/Klaviyo setup and recommend Klaviyo vs. a lighter Shopify-first path.

Confirm current tools, account access, plan limits, and whether SMS should be included in phase one.

Approved platform path.

Consent + list prep

Identify marketing-consented Shopify customers, separate non-consented customers, and define initial segments.

Confirm which existing customers can be messaged and provide privacy/terms links needed for signup forms.

Consent-ready audience setup.

Market opt-in funnel

Build the signup path: QR destination, form/page, source tags, first offer code, welcome message, and SMS consent language if used.

Approve offer, SMS use, landing copy, and required brand/customer language.

Live opt-in funnel for pilot markets.

Offer strategy

Recommend first offer options, such as pizzetta deal, pre-reserve test, threshold discount, or free add-on.

Set margin guardrails, inventory constraints, and products that are realistic to promote.

First pilot offer and testing plan.

Market assets

Create trackable Market QR Codes, lid sticker CTA copy, booth CTA copy, and print-ready handoff.

Choose 2-3 pilot markets, confirm market rules, approve copy, and handle printing.

Lid Stickers + Market QR Codes ready for launch.

Launch QA

Test QR codes, form submission, source tagging, consent status, discount code, and welcome message.

Review and approve the live flow before it goes to market.

Launch-ready capture system.

Summer activation

Recommend weekly specials, pre-reserve tests, and offer adjustments based on early engagement; lead a 45-minute weekly sync if retained for activation support.

Share market calendar, product availability, staff feedback, and approve weekly messages/offers.

Active summer learning loop.

Measurement

Track opt-ins, source tags, clicks, redemptions, unsubscribes, first online orders, and delivery-interest signals.

Share booth observations and operational context that the numbers do not capture.

Simple performance dashboard and learning notes.

Fall delivery transition

Turn summer engagement into a personalized fall delivery offer, freezer-stock bundle, or recurring order test.

Confirm delivery capacity, product/bundle options, fulfillment constraints, and offer economics.

Fall delivery transition plan.

Success Benchmarks

Initiative

Metric

Baseline

Pilot Target

Measured In

Lid Stickers + Market QR Codes

New market opt-ins as a share of POS orders

No active booth capture system; historical known POS order share is 8.38%

15-20% opt-in rate at pilot markets

Email/SMS source tags + Shopify POS counts

Email/SMS consent flow

New email/SMS opt-ins

No unified capture flow

Clear weekly opt-in count by market

Email/SMS list growth and consent status

Monthly summer offers

Click rate + redemption rate

Not currently tracked by market list

Identify one offer that earns repeat response

Email/SMS clicks + Shopify discount usage

Market-to-online transition

First online order from market signups

Not currently tracked from new market signups

Drive first online orders before the fall delivery push

Shopify order source + customer profile history

Fall delivery offer

Delivery bundle purchases or recurring offer signups

New test

Validated fall offer before markets slow down

Shopify products, discounts, and email/SMS campaigns

Pricing Structure To Discuss

Phase

Planning Range

Notes

Current audit / data dive

$500

About 8 hours of audit work: data cleaning, order-level revenue correction, customer segmentation, findings, and pilot recommendations.

Phase 1: Prep + Capture Infrastructure

$1,500-$2,500

Final price depends on Klaviyo status, SMS needs, number of pilot markets, offer setup, QR/sticker funnel complexity, welcome flow, and dashboard depth.

Phase 2: Summer Experimentation

$1,000-$1,500/month if I own weekly support

Applies if I help with weekly specials, pre-reserve tests, unsubscribe monitoring, reporting, offer learning, optimization during market season, and a 45-minute weekly sync.

Phase 3: Fall Delivery Conversion

Scope after summer learnings

Can be scoped as a project or included in the activation retainer depending on how much campaign/build work is needed.

Client costs

Separate

Klaviyo/software, print assets, and offer/discount budget are separate from my implementation work.

Later media tests

Save for later

Retargeting or lookalike tests should wait until the list is larger and the fall offer is proven.

Inputs Needed Before Final Quote

•	
      Shopify access or a current export.

•	
      Klaviyo access/status, if Klaviyo is already installed.

•	
      Decision on SMS for phase one.

•	
      Pilot market list.

•	
      Market rules around stickers, QR codes, and signage.

•	
      First offer budget and margin guardrails.

•	
      Print quantity and asset timing.

•	
      Delivery/fall fulfillment constraints.

Suggested Next Step

The main thing to decide first is whether this pilot is worth scoping. If yes, the next deliverable is a tighter implementation scope with final platform recommendation, launch timeline, three-phase pilot plan, exact responsibilities, final setup budget, optional summer activation support, and the inputs needed to launch at the first pilot markets.